## Blad1
ID | Priority | As a(n) | I want to be able to | So that | Estimation | Sprint | Status
1 | 1 | Visitor | Visit the homepage and understand the purpose of the website | I can take action accordingly | small | 1 | Done
2 | 2 | Visitor | Navigate the website easily | I can find what I need quickly | small | 1 | Done
9 | 3 | Visitor | Read general information about the meaning of AI | I can better understand the implications of AI | medium | 1 | Done
3 | 4 | All | Find the website in the top google seach results | I can get what I was looking for | big | 1 | Done
5 | 5 | All | Find AI advertisements that suit my interests | I can learn more about the product/service | big | 1 | In progress
4 | 6 | Visitor | Search through various article subjects in the Blog | I can find a article on a specific subject of interest | small | 1 | Done
17 | 7 | AI Student | I want to discover various AI challenges | I can apply | small | 1 | Done
6 | 8 | Business owner/visitor/start-up | Read articles about the benefits that AI services can have for my business | I can take action accordingly | medium | 1 | In progress
18 | 9 | AI Student | I want to be able to search trough the available challenges | I can find out which ones I can apply to | medium | 1 | Done
7 | 10 | Business owner | Learn what AI technology is and what it means for the future | Better understand the implications of AI | big | 1 | In progress
8 | 11 | Business owner | Learn about AI service providers that can enhance my business | I can discover useful services | big | 1 | In progress
28 | 10 | AI Student | Read articles about interesting topics from within the AI industry | I can discover my topics of interest (for an internship/project) | medium | 1 | Done
12 | 11 | Start-up | Understand how I can place my challenge on the website | I can send my AI challenge for publishing | medium | 2 | Done
13 | 12 | Start-up | Understand the requirements for a challenge | I can comply when drafting my AI challenge | big | 2 | Done
20 | 13 | AI Student | Know how to contact the person who is responsible for the challenge | I can take action accordingly | medium | 2 | Done
15 | 14 | Start-up | Know how the students will apply and how to be in contact with them | I know what to expect and how to engage with the students | small | 2 | Done
14 | 15 | Start-up | See the format in which my challenge will be presented or communicated | I can judge whether it is the right format for me | medium | 2 | Done
24 | 16 | AI Student | Can read more about the AI start-up behind the challenges | I can learn more about who I would be working for | small | 2
29 | 17 | AI Student | Know what I need to send | Apply for the challenge | small | 2
30 | 18 | AI Student | Make a varied choice in terms of challenges | I can choose a challenge that I'm interested in. | big | 2
31 | 19 | AI Student | Apply to a mailing list | I can keep up to date with new challenges. | medium | 2
23 | 20 | AI Student | Can login with linkedin/github/kaggle | I can show my expertise on the website | medium/big
22 | 21 | AI Student | Can create an account | I can use the services provided by the website in a more consistent way | medium
19 | 22 | AI Student | Apply to a challenge with my account | I can get in contact with the challenge owner. | medium
11 | 23 | Start-up | Register my start up with an account | I can use the service provided by the website | medium
25 | 24 | AI Student | Let my account becomes visible in google searches on my name | I can showcase my engagement with the website | big
26 | 25 | AI Student | Get notification when there is a response from the challenge owner | I can take action accordingly | big
28 | 26 | Start-up | Get notification when there is a response from students | I can respond
27 | 27 | Start-up | Create a private and public account | I can publish my project directly onto the site | medium
32 |  | As UvA students we completed all the parts of the projects and comply with the advanced requirements
project/job/internship = challenge
| Small (1 pt) | Medium (2 pts) | Big (3pts) | Totaal
Sprint 1 | 3.5 | 5 | 4.5 | 13
Sprint 2 |  |  |  | 0
Sprint 3 |  |  |  | 0
49