## Sheet1
ID | Priority | User story | Task | It's done when | Status
32 | 1 | As UvA students we completed all the parts of the projects and comply with the advanced requirements | Finish rapport w.r.t advanced requirements. | Processed feedback and sended best version for grading. | In progress
| Big |  | Finish the final presentation w.r.t advanced requirements. | Have a presentation that complies and execute on Friday. | In progress
34 | 2 | As a user of the AI marketspace website I want to be able to use the website without any trouble or discomfort. All my actions are taken into account and there are no design flaws. | - All the functional components work as intended (buttons etc) | All functional components work as intended. | Done
| Medium |  | - Website is dummy proof and intuive. | Dummies have tested the website and declared it intiutive. | In progress
|  |  | - All details are in order, there are no design flaws in whatever setting the website can be found in. | Design is flawless and works on all devices. All text is clear and error free. All hyper links and names are logical and correct. | Done
5 | * | As a Visitor I want to find AI advertisements that suit my interests so that I can learn more about the product. | - Enable adding ads with google Adsense | Adsense is installed in Wordpress | Done
| Big |  | - Choosing good location on the webpage for our ads. | Ads show up in specified locations | Done
|  |  | - Adjust adsense parameters to filter ads | Visitors only get technology ads, no NSFW | Done
|  |  | - Also works on non smart phone devices | Ads pop up on non mobile devices visiting our website | In progress
31 | 3 | As an AI Student I want to apply to a mailing list so that I can keep up to date with new challenges. | - Create contact form which allows users to apply | Contact form is accessible and functions correctly. | Done
| Medium |  | - Create confirmation email when user signs up | Confirmation email is sent succesfully and contains relevant info. | Done
|  |  | - Create ability to sing out of mailing list via link | Each mail from mailing list contains working unsubscribe button. | Done
33 | 5 | As one of the AI marketspace owners I want to be able to follow the outreach campaign with ease so I can take appropriate steps when needed. | - Create a contact sheet for tracking the outreach efforts | The sheet works as intended and contains the needed information. | Done
| Medium |  | - Determine the best protocol for tracking the efforts | The protocol makes our outreach campaign effective and keeps it organized. | Done
|  |  | - Create a comprehensive list of AI companies we want to reach out to | Have a list of at least 100 potential AI companies to reach out to. | In progress
30 | 6 | As an AI Student I want to make a varied choice in terms of challenges so that I can choose a challenge that I'm interested in. | - Reach out to at least 40 potential start-ups to place their challenge on our website. | We have sent 40 outreach emails to potential start-ups. | In progress
| Big |  | - Add the acquired challenges on our website. | All accepted challenges show up on our website.