## Sheet1
ID | Priority | User story | Task | It's done when | Status
1 | 1 | As a Visitor I want to visit the homepage and understand the purpose of the website so that I can discover AI marketspace | - create clear and sensible layout | All parts are structured sensibly | Done
| Medium |  | - write short and grabbing texts | Every part has a custom informative text | In progress
|  |  | - use pictures to make page less boring | Pictures are placed where needed | Done
2 | 2 | As a Visitor I want to navigate the website easily so that I can find what I need quickly | - create logical top menu | Menu is responsive and links to pages | Done
| Medium |  | - create links and buttons for navigation | All buttons respond to their destination | Done
|  |  | - create sensible footer with extra functions | Extra functionality is listed in the footer
9 | 3 | As a business owner/ start-up/ visitor I want to read general information about the meaning of AI so I can understand how and when to use it. | - Blog contains an article about AI and its role in business. | Blog page is created and typed out.
| Medium |  | - Create a page with general information about the development of AI | Page contains informative text and images | Done
3 | 4 | As a Visitor I want to find the website on google so that I can get to what I was looking for | - Make homepage crawler friendly | SEO plugins shows no problems | Done
| Big |  | - Show different blog posts in google | Blogs are keyword optimized | In progress
|  |  | - Show main page on google | Custom text is shown in SERP | Done
5 | 5 | As a Visitor I want to find AI advertisements that suit my interests so that I can learn more about the product. | - Enable adding ads with google Adsense | Adsense is installed in Wordpress | Done
| Medium |  | - Choosing good location on the webpage for our ads. | Ads show up in specified locations | In progress
|  |  | - Adjust adsense parameters to filter ads | Visitors only get technology ads, no NSFW | In progress
4 | 6 | As a Visitor I want to search throug various article subject so I can find an article on a specific subject | - Blog page contains search bar that searches exclusively through the articles. | Search bar is available and functioning | Done
| Small |  | - Define subjects and categories and apply this to article pages. | Every article has a category attached | Done
17 | 7 | As an AI student I want to discover AI challenges so that I can gain or showcase my experience. | - Make Market page easy to find | Project page is available and reachable at any time | Done | In progress
| Small |  | - There is clear intructions or it is clear how the Market works.
|  |  | - The Market project page design gives a clear overview of the available challenges. |  | Done
6 | 8 | As a visitor I want to read articles about the benefits that AI services can have so I can consider using them | - Write articles about general AI services | 3 short articles are written about consumer AI services
| Medium |  | - Make articles visible in homepage | Articles show up and can be found
18 | 9 | As an AI student I want to be able to search through the available challenges so that I can find out which ones I can apply to | - There is a search bar that searches only through challenges. | Search bar is adjusted in such a way to mee this requirement. | Done
| Medium |  | - Each project has their own page. | Webpage with more details about the project, placeholder. | Done
7 | 10 | As a Business owner I want to learn what AI technology is and what it means for the future so that I can better understand the implications of AI | - The blog contains articles that contains this information.
| Medium |  | - The homepage makes this clear.
8 | 11 | As a Business owner I want to Learn about AI service providers that can enhance my business so that I can discover useful services | - Create informative pages about AI service providers. | 3 articles available in the blog.
| Medium |  | - contact AI service providers for listing them on our website | 3 providers have agreed to be listed.