## Sheet1
ID | Priority | User story | Task | It's done when | Status
1 | 1 | As a Visitor I want to visit the homepage and understand the purpose of the website so that I can discover AI marketspace | - create clear and sensible layout | All parts are structured sensibly | Done
| Medium |  | - write short and grabbing texts | Every part has a custom informative text | Done
|  |  | - use pictures to make page less boring | Pictures are placed where needed | Done
5 | 2 | As a Visitor I want to find AI advertisements that suit my interests so that I can learn more about the product. | - Enable adding ads with google Adsense | Adsense is installed in Wordpress | Done
| Big |  | - Choosing good location on the webpage for our ads. | Ads show up in specified locations | In progress
|  |  | - Adjust adsense parameters to filter ads | Visitors only get technology ads, no NSFW | In progress
28 | 3 | As an AI student I want to read articles about interesting topics from within the AI industry so that I can discover topics of my interest. | - Write interesting articles about various AI topics | About 10 blogs are written and visible on the website | In progress
| Medium |  | - Classify blogs based on subject | All available blogs contain a applicable category | In progress
|  |  | - Optimize blogs for search engines | Each blog scores OK for SEO in plugin | In progress
12 | 4 | As a Start-up I want to understand how I can place my challenge on the website so that I can send my AI challenge for publishing. | - Decide on the process how challenges will be placed. | A communication protocol (CP) document is available for us only, containing information about the contact method
| Medium |  | - Describe the process in details on the website. | A page is available for businesses containing information about the process of contacting us
13 | 5 | As a Start-up I want to understand the requirements for a challenge so that I can comply when drafting my AI challenge. | - Define the minimal requirements for each kind of challenge. | The CP document containing the information we need to post a challenge on the website
| Big |  | - Describe the details about the requirements in our outreach mail. | A format for our outreach mail is specified which contains these details
20 | 6 | As an AI Student I want to know how to contact the person who is responsible for the challenge so that I can take action accordingly. | - Decide on the communication protocol between students and start-ups. | The CP document contains the decisions we have made regarding this.
| Medium |  | - Inform students about information they need to send when applying. | Aforementioned document contains this overview.
|  |  | - Describe the process on the website for the students. | Website has a comprehensive version of the aforementioned document
15 | 7 | As a Start-up I want to know how the students will apply and how to be in contact with them so that I know what to expect and how to engage with the students. | - Describe Communication Protocol in mails to start-ups. | Outreach mail contains said information.
| Small |  | - Decide on the flexibility with regards to extra services the start-up might desire. | CP document describes this.
14 | 8 | As a Start-up I want to see the format in which my challenge will be presented or communicated so that I can judge whether it is the right format for me | - Create placeholder challenge which shows relevant information for start-ups. | The challenge page is done and reachable.
| Medium |  | - Specify customisability of challenge page. | Placeholder challenge contains said information at the end
|  |  | - Create link to application information. | Placeholder challenge has a button which links to application info
24 | 9 | As an AI Student I want to read more about the AI start-up behind the challenge so that I can learn more about who I would be working for. | - Create page for start-ups showing information about said business. | Start-up page is designed and online.
| Small |  | - Enable intuitive action to show more information about a start-up. | Action is logical and directs to correct page.
29 | 10 | As an AI Student I want to know what I need to send to the challenge owner so that I can apply for the challenge. | - Decide on the basic requirements. | - Requirements are in the CP document.
| small |  | - Describe required information for applying on website | - Page containing relevant information is created.
|  |  | - It is easy to find out about the needed aformentioned requirements. | - Relevant pages for challenges contain link to application info
30 | 11 | As an AI Student I want to make a varied choice in terms of challenges so that I can choose a challenge that I'm interested in. | - Reach out to at least 40 potential start-ups to place their challenge on our website. | We have sent 40 outreach emails to potential start-ups.
| big |  | - Add the acquired challenges on our website. | All accepted challenges show up on our website.
|  |  | - Test the challenge overview page and page itself with students | Students have gone through our website and given feedback.
31 | 12 | As an AI Student I want to apply to a mailing list so that I can keep up to date with new challenges. | - Create contact form which allows users to apply | Contact form is accessible and functions correctly.
| Medium |  | - Create confirmation email when user signs up | Confirmation email is sent succesfully and contains relevant info.
|  |  | - Create ability to sing out of mailing list via link | Each mail from mailing list contains working unsubscribe button.